## Tasks Log
When |  |  |  | What |  | Who
Date | Time |  | Time Spent | Task | Details | Name | Comments
| Start | End | (hours)
|  |  | 1 hour | Model | - Created models: TaskListManager, TaskList, TaskItem | Faye
|  |  | 3 hours | User Interface | - activity_task_list and list_item layout | XIRAN
2016-02-19 |  |  | 4 hours | Database Model | - Added DB model/schema and addTask | Paul | See add-list-item on upstream for commits
2016-02-20 |  |  | 6 hours | Database Model | - Model refinement, ArrayAdaptor onboarding | Paul | Custom ArrayAdaptor required for ListView
2016-02-21 |  |  | 4 hours | Check-off Item | - give task item a checkbox | Bailey | working on local branch check_off_item
2016-02-21 |  |  | 8 hours | Add-Item | - ArrayAdaptor completed, add functionality completed | Paul | Work missing unit tests only at this point
2016-02-21 |  |  | 4 hours | Delete-item | -delete task item from a database and a list | Lam | working on local branch lamdoan-delete-task-lits-item

## Meetings Log
When |  |  | Where | What | Who
Date | Time |  | Location | Description | Attendees
| Start | End
2016-01-11 | 14:30 | 15:30 | E2 tables | - Set up Slack and Asana | Faye | Paul |  |  | Bailey
- Planned the next meeting
2016-01-13 | 14:30 | 16:00 | E2 tables | - Came up with ideas for the apps: to-do list or expense tracking | Faye | Paul | Lam | Xiran
- Looked for potential customers
- Brainstormed some interview questions for Friday interview
2016-01-15 | 14:30 | 17:00 | E3-362D (Library group study room) | - Met the customer | Faye | Paul | Lam | Xiran
- Discussed the project with customer and the customer chose To-do List
- Practiced going over some questions with customer before filiming several times
- Filmed a 20-mins interview video
- Wrote down some user stories while interviewing.
- Discussed the priority for each user story with a customer
2015-01-20 | 14:30 | 17:30 | E3-362D | - Planned and organized user stories | Faye | Paul | Lam | Xiran | Bailey | Matt
- Estimated the cost of developing each story
2015-01-22 | 14:30 | 17:15 | E3-362D | - Finalized iteration 0 | Faye | Paul | Lam | Xiran | Bailey
- Assigned tasks to each member.
2016-02-03 | 14:30 | 17:15 | E3-362D | - Resolved GitHub issues, resolved build issues, and got everybody on github | Faye | Paul | Lam | Xiran | Bailey
- Made all group members create a fork off of the main project.
- Started testing of merging project together.
- Resolved issues with repo's, deleted all forks and reforked and recloned our project
2016-02-05 | 14:30 | 17:15 | E3-362D | - Solved possible conflicts within Github | Faye | Paul |  | Xiran | Bailey | Matt
2016-02-10 | 14:30 | 17:15 | E3-362D | - Got version control to work for the group | Faye | Paul | Lam | Xiran | Bailey | Matt
- Made Git path to the proper area for version control
- Set up forks for all group members
2016-02-12 | 14:30 | 17:15 | E3-362D | - Solved possible conflicts within Github | Faye |  | Lam | Xiran | Bailey | Matt
2016-02-17 | 14:30 | 18:00 | E3-362D | - Got all conflicts with merging sorted. | Faye | Paul | Lam | Xiran | Bailey
- Added button images for delete and add items (in a mipmap vs drawable)
- All team members have their own branches off the main upstream (root) branch
- Discussed more about git, and how we’re going to implement version control
(just using the Git Shell vs using Android Studio’s built in version control).
2016-02-22 | 14:30 | 17:30 | E3-362C | - Finalized iteration 1 | Faye | Paul | Lam |  | Bailey
- Added the architecture diagram to the upstream
- Merge all of the possible finished code from different branches into the upstream
2016-02-24 | 14:30 | 17:30 | E3-362D | - Merged check_off_item branch and lamdoan-delete-task-lits-item branch with master branch |  | Paul | Lam | Xiran | Bailey | Matt
- Looked for some potential bugs
2016-02-29 | 14:30 | 17:30 | Room 223A (Science Library) |  | Faye | Paul | Lam |  | Bailey
2016-03-09 | 14:30 | 17:30 | Room 360 (Science Library) | - Revised planning for iteration 2 |  | Paul | Lam |  | Bailey

## Upcoming meetings
Upcoming Meetings
Meeting date | Room# | Meeting location | From | To
Wednesday, March 9, 2016 | Room 360 | Science library | 14:30 | 17:30
Friday, March 11, 2016 | Room E3-362D | Engineering library | 14:30 | 17:30
Monday, March 14, 2016 | Room 223A | Science library | 14:30 | 17:30
Wednesday, March 16, 2016 | Room 223A | Science library | 14:30 | 17:30
Friday, March 18, 2016 | Room 223A | Science library | 14:30 | 17:30
Monday, March 21, 2016 | Room 223A | Science library | 14:30 | 17:30
Wednesday, March 23, 2016 | Room 223A | Science library | 14:30 | 17:30
Friday, March 25, 2016 |  |  | 14:30 | 17:30
Monday, March 28, 2016 |  |  | 14:30 | 17:30
Wednesday, March 30, 2016 |  |  | 14:30 | 17:30
Friday, April 1, 2016 |  |  | 14:30 | 17:30
Monday, April 4, 2016 |  |  | 14:30 | 17:30
Wednesday, April 6, 2016 |  |  | 14:30 | 17:30
Friday, April 8, 2016 |  |  | 14:30 | 17:30